## Main
Project | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint # | Start | End | Status | Work / Estimates Committed | Work spent Delivered | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 | 2025-02-12 | 2025-02-19 | Complete | 4 | 4
[6 empty] | 2 | 2025-02-22 | 2025-03-01 | In Progress
[6 empty] | 3 | 2025-03-04 | 2025-03-11 | In Progress
[6 empty] | 4 | 2025-03-14 | 2025-03-21 | In Progress
[6 empty] | 5 | 2025-03-24 | 2025-03-31 | In Progress
Formulas:
Project #1 = [Start]+7
Start = [Project #1, row above]+3

## Sprint 1 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
[7 empty] | Remaining work to be done. | Total number of hours you spent on the task. Your effort | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
1.1 | SW-1 | Thiết kế UI Đăng bài | Thảo | Done | 3 | 3 | 0 | 3 | 0 | Day 1: 3
1.2 | SW-2 | Code FE đăng bài | Thảo | Ongoing
1.3 | SW-3 | Thiết kế UI đăng ký quyên góp | Tiên | Done | 6 | 6 | 0 | 4 | -2 | Day 2: 2; Day 3: 2; Day 4: 2
1.4 | SW-4 | Code FE đăng kí quyên góp | Tiên | Ongoing
1.5 | SW-5 | Thiết kế UI theo dõi trạng thái | Nguyên | Done | 4 | 4 | 0 | 3 | -1 | Day 5: 3; Day 6: 1
1.6 | SW-6 | Code FE theo dõi trạng thái | Nguyên | Ongoing | 4 | 4 | 0 | 3 | -1 | bar: Day 4 to Day 7
1.7 | SW-7 | Thiết kế UI liên hệ tổ chức | Thành | Done | 3 | 0 | 0 |  | -3
1.8 | SW-8 | Code UI liên hệ tổ chức | Thành | Ongoing |  | 0 | 0 |  | 0
1.9 | SW-9 | Thiết kế UI Home page | Thúy | Done | 3 | 0 | 3 |  | -3
1.91 | SW-10 | Code FE Home page | Thúy | Ongoing |  | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
|  |  |  | Total | 23 | 17 | 3 | 13 | -10 | 3 | 2 | 2 | 3 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 20 | 18 | 16 | 13 | 9 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
|  |  |  | Burn up | [5 empty] | 3 | 5 | 7 | 10 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
Note on B7: ====== ID#AAABeAaZfdk jan samuelsson (2025-02-12 11:35:22) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAABeAaZfdY jan samuelsson (2025-02-12 11:35:22) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.
Note on H7: ====== ID#AAABeAaZfdc jan samuelsson (2025-02-12 11:35:22) Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.