## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Đăng ký. | Là Khách | Đăng ký. | Tôi có thể đăng ký tài khoản mới để đăng nhập vào hệ thống. | - Tài khoản phải >8 ký tự, <16 ký tự chữ và số, không chứa ký tự đặc biệt 'Sử dụng email hợp lệ 'Sử dụng sđt di động hợp lệ |  | 1 |  |  |  | 1 | 10
PB02 | Đăng nhập | Là Khách | Đăng nhập | Tối có thể đăng nhập lại nếu như tôi đã đăng ký trước đó
PB07 | Investigate communication | Make a prototype to investigate how to configure the communication between back- and front-end
Note on M7: jan samuelsson: Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.

## Main
Project | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint # | Start | End | Status | Work / Estimates Committed | Work spent Delivered | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 | 2019-01-07 | 2019-01-18 | Complete | 3 | 3
[6 empty] | 2 | 2019-01-21 | 2019-02-01 | Complete | 25 | 23
[6 empty] | 3 | 2019-02-04 | 2019-02-15 | Complete | 20 | 18
[6 empty] | 4 | 2019-02-18 | 2019-03-01 | Complete | 25 | 13
[6 empty] | 5 | 2019-03-04 | 2019-03-15 | In Progress | 20
Formulas:
Project #1 = [Start]+11
Start = [Project #1, row above]+3

## Sprint 1 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
[7 empty] | Remaining work to be done. | Total number of hours you spent on the task. Your effort | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
1.1 | PB01 | Thiết kế UI đăng ký tài khoản | Long | Done | 3 | 3 | 0 | 5 | 2 | Day 1: 3
1.2 | PB01 | Xây dựng module kiểm tra tính hợp lệ các trường dữ liệu | Dũng | Not started | 6 | 6 | 0 |  | -6 | Day 2: 3; Day 3: 3
1.3 | PB01 | Develop CSS/HTML | Bình | Done | 3 | 4 | -1 | 10 | 7 | Day 4: 4
1.4 | PB01 | Lập trình |  | Done | 10 | 10 | 0 | 4 | -6 | Day 5: 4; Day 6: 3; Day 7: 3
1.5 | PB01 | Viết test case |  | Done | 3 | 4 | -1 | 20 | 17 | Day 7: 3; Day 8: 1
1.6 | PB01 | Test & Fix |  | Ongoing | 3 | 3 | 0 | 2 | -1 | Day 8: 3
1.7 | PB02 | Code & test |  | Done | 20 | 5 | 15 | 25 | 5 | Day 12: 5
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
|  |  |  | Total | 48 | 35 | 13 | 66 | 18 | 3 | 3 | 3 | 4 | 4 | 3 | 6 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 45 | 42 | 39 | 35 | 31 | 28 | 22 | 18 | 18 | 18 | 18 | 13 | 13 | 13 | 13
|  |  |  | Burn up | [5 empty] | 3 | 6 | 9 | 13 | 17 | 20 | 26 | 30 | 30 | 30 | 30 | 35 | 35 | 35 | 35
Note on B7: jan samuelsson: 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: jan samuelsson: Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.
Note on H7: jan samuelsson: Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 2 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  | Only update one time. When task is done.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
Remaining
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
2.1 | PB0x |  |  |  |  | 0 | 0
2.2 | PB0x |  |  |  |  | 0 | 0
2.3 | PB0x |  |  |  |  | 0 | 0
2.4 | PB0x |  |  |  |  | 0 | 0
2.5 | PB0x |  |  |  |  | 0 | 0
2.6 | PB0y |  |  |  |  | 0 | 0
2.7 | PB0y |  |  |  |  | 0 | 0
2.8 | PB0y |  |  |  |  | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn up |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms